## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Light
E-commerce
Company name | Group16 |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead | Chloe
Project Start Date: | 2021-09-20 |  |  |  |  | September | [13 empty] | October | [27 empty] | November
Scrolling Increment: | 3 | time axis 2021-09-23 to 2021-11-17
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2021-09-23 to 2021-11-17
Iteration01
Iteration planning and meeting | Goal | Chloe | 75% | 2021-09-20 | 2
Complete stakeholder register | Low Risk | Chloe,Stella | 100% | 2021-09-21 | 1
Design persona | On Track | Chloe,Stella,Cookie | 50% | 2021-09-22 | 5
Review and test persona | Med Risk | Chloe,Cookie | 90% | 2021-09-27 | 2
Complete progress report | Milestone | Chloe,Stella,Cookie,Olivia | 100% | 2021-09-30 | 3 | bar: 2021-09-30 to 2021-10-02
Iteration02
Iteration planning and meeting | Goal | Stella | 60% | 2021-10-02 | 13 | 2021-10-02: 2; 2021-10-03: 2; 2021-10-04: 2; 2021-10-05: 2; 2021-10-06: 2; 2021-10-07: 2; 2021-10-08: 2; 2021-10-09: 2; 2021-10-10: 2; 2021-10-11: 2; 2021-10-12: 2; 2021-10-13: 2; 2021-10-14: 2
Complete resource needs | On Track | Chloe,Stella | 50% | 2021-10-09 | 2
Review the resource needs | Low Risk | Olivia | 95% | 2021-10-14 | 1
Complete Gantt chart | On Track | Chole | 30% | 2021-10-16 | 20
Complete progress report | Milestone | Stella | 50% | 2021-10-21 | 9 | bar: 2021-10-21 to 2021-10-29
Iteration03
Iteration planning and meeting | Goal | Chloe | 30% | 2021-10-26 | 14 | 2021-10-26: 2; 2021-10-27: 2; 2021-10-28: 2; 2021-10-29: 2; 2021-10-30: 2; 2021-10-31: 2; 2021-11-01: 2; 2021-11-02: 2; 2021-11-03: 2; 2021-11-04: 2; 2021-11-05: 2; 2021-11-06: 2; 2021-11-07: 2; 2021-11-08: 2
Complete risk register | Med Risk | Chloe,Stella | 90% | 2021-10-29 | 2
Complete user acceptance tests | On Track | Chloe,Stella,Cookie,Olivia | 80% | 2021-11-05 | 6
review the risk register and the UAT | Milestone | Chloe | 30% | 2021-11-10 | 3 | bar: 2021-11-10 to 2021-11-12
Complete progress report | Milestone | Chloe,Stella,Cookie,Olivia | 90% | 2021-11-09 | 1 | bar: 2021-11-09